## Sheet1
Generic Responsibility Matrix
Responsible Parties |  |  |  |  | Level of Information Need |  |  |  |  | A template provided by:
Ref | Description | Organisation |  |  | 1: Statement of requirements of project (Project Brief)
A | Architect |  |  |  | 2: Initial response to the Project Brief including outline performance requirements and spatial requirements
B | Building surveyor |  |  |  | 3a: Dimensionally correct and spatially coordinated design information aligned to the Project Brief
C | Civil engineer |  |  |  | 3b: Spatially coordinated design and associated performance specification aligned to the Project Brief
D | Drainage, highways engineer |  |  |  | 4: Full design information meeting the Project Brief, fully coordinated and suitable for manufacture and construction
E | Electrical engineer |  |  |  | 5: As-constructed information
F | Facilities manager
G | Geographical and land surveyor |  |  |  | Responsibilities
H | Heating and ventilation designer |  |  |  | L: Lead and Coordinate
I | Interior designer |  |  |  | D: Design and Model
K | Client |  |  |  | A: Advise
L | Landscape architect
M | Mechanical engineer |  |  |  | IMPORTANT NOTES:
P | Public health engineer |  |  |  | 1) This Responsibility Matrix is a generic matrix and is intended to provide an example and a prompt for the various items which should
Q | Quantity surveyor |  |  |  | be considered as part of the structural design for a project. It is recognised that not all items will apply to all projects, and the list
S | Structural engineer |  |  |  | provided here will not be comprehensive to cover all aspects of all projects.
T | Town and country planner |  |  |  | 2) During Stage 2, the Responsibility Matrix should be developed specific to the project requirements. This should then continue to be
W | Contractor |  |  |  | reviewed and updated as the structural design develops. The aim is always to provide clarity of who is responsible for which part of the
X1 | Subcontractor 1 |  |  |  | project, and the level of information expected at each stage.
X2 | Subcontractor 2 |  |  |  | 3) The Lead Designer has overall responsibility for co-ordination and the structural engineer only has responsibility to integrate with
Y1 | Specialist designer 1 |  |  |  | other disciplines and co-ordinate within own discipline.
Y2 | Specialist designer 2 |  |  |  | 4) For components such as glazing and balustrades it is helpful to show that the structural engineer may only be providing limited
Z1 | Design Lead |  |  |  | structural information.
Z2 | Project Lead
|  | Stage 2 |  | Stage 3 |  | Stage 4 |  | Stage 4.5 |  | Stage 5
|  | Concept Design1 |  | Spatial Coordination1 |  | Technical Design1 |  | Production Design |  | Manufacturing and Construction1
Description |  | Responsible Party | Level of Information Need | Responsible Party | Level of Information Need | Responsible Party | Level of Information Need | Responsible Party | Level of Information Need | Responsible Party | Level of Information Need
Surveys and existing structures
Topographical surveys
Site investigation
Condition survey
Load assessment of existing structures
Strengthening of existing structures
Party wall surveys
Ground contamination survey
UneXploded Ordinance assessment
Additional surveys
Site Preparation
Site formation levels and sub base
Cut and fill
Demolition and site clearance
Diversion of existing drainage networks
Ground improvement
Incoming services
Foundations and Groundworks
Loading criteria
Structural movements
Strip and pad foundations
Precast concrete foundations
Pile foundations
Pile caps and ground beams
Ground bearing slabs
Retaining walls
Reinforcement detailing of substructures
Waterproofing below ground slab level
Water retaining structures
Gas protection measures
Ground movement protection measures
Coordination of below ground services
Superstructure
Loading criteria
Structural movements
Structural steelwork
Steelwork connections
Steel to concrete connections
Steelwork corrosion protection
In situ reinforced concrete frame
Reinforcement detailing and bending schedules
Precast structural concrete
Prestressed concrete
Metal decking
Structural toppings
Floor pits, chambers, trenches and recesses
Lift pits
In situ concrete staircases / ramps
Movement joints in structure
Major structural penetrations
Cold formed sections
Structural timber
Proprietary timber elements
Structural masonry
Secondary support to services and plant
Plant plinths and bases
Structural bearings
Roofing, Cladding, Walling, Facades
Secondary steelwork
Wind posts
Masonry restraint details
Structural framing to openings in cladding / masonry
Wall ties
Lintels
Movement joints
Non-loadbearing walls / partitions
Curtain walling
Glazing
Architectural metalwork
Balconies
External Works
Land drainage
Irrigation systems
External works levels
Access routes / roads
Car parks - location and layout
Pavements, pacing, kerbs and steps / ramps
External groundworks - excavation, filling, re-grading
External groundworks - soil stabilisation
Tie-in to existing construction
Retaining walls - masonry
Retaining walls - concrete
Proprietary retaining walls
Non-standard concrete chambers, ducts, gratings, trenches
External handrails, balustrades, parapets
Fences, gates, bollards etc
Vehicle movements and turning circles
External signage, line markings
Earthing pits
Free standing enclosures
Pre-fabricated buildings / structures
Vehicle and people barriers
Car park barriers
Tree protection
New road junctions / connection to existing highways
Alterations to existing road junctions
Drainage Systems
Surface water drainage - below lowest floor slab
Surface water drainage - above lowest floor slab
Foul water drainage - below lowest floor slab
Foul water drainage - above lowest floor slab
Interceptors, attentuation tanks
Soakaways
New connections / outfalls to drainage networks
Design Assurance
Design reviews of structural principles
Structural calculation checking
Review of specialist sub-contractor designs
Review and checking of manufacturing information
Review of construction quality testing
Snagging and structural defects identification
Temporary Works
Temporary works requirements
Methods of erection
Definition of preset geometries / precambering
Miscellaneous
Grid setting out
Floor levels
Party wall agreement
Adjoining neighbours
Fire protection
Coordination of builder's work
Cast in conduits, pipes and sleeves
Cast in inserts, hooks and bolts
Lift guide rails etc.
Floors within risers
Barriers for vehicles / people
Handrails, balustrades, parapets
Access walkways / ladders
Proprietary steel access / escape stairs
Floating floors and acoustic isolation / bearings
Cleaning access equipment supports
Duct and chamber covers and gratings
Lightning protection
Project Management
Responsibility Matrix
Project Programme
Design Programme
Exchange Information Requirements (EIR)
Project Execution Plan
Pre-Construction Information
Planning Application
Building Regulations Application
Reference: 1 RIBA Plan of Works 2020